SMART PARKING PLATFORM

Homework 5: Roles & Resources, Cost Plan,

and RACI Matrix

Prepared by: WE ARE $oftware ¢orp.

Muhammad Murtaza

CIS 4374 19148

October 8, 2026

# 8. Roles & Resources

The project team is made up of eleven people with roles that map to the teams in the WBS and all the names, skill levels, and rates are planning assumptions. Hours are calculated as FTE % × 640 hours (40 hours per week over the 16-week semester).

## 8.1 Skill Level Assumptions

- Senior: 8+ years of experience, the lead design decisions and mentor others.

- Mid: 3–7 years of experience, work independently on assigned work packages.

- Junior: 0–2 years of experience, work with regular review and guidance.

## 8.2 Resource Plan

| Role | Name | Skill Level | FTE % | Est. Hours | Hourly Rate | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Project Manager | Maya Patel | Senior | 50% | 320 | $75 | $24,000 |
| Business Analyst | Omar Haddad | Mid | 40% | 256 | $60 | $15,360 |
| Backend/API Lead | Daniel Kim | Senior | 100% | 640 | $80 | $51,200 |
| Backend/API Developer | Priya Nair | Mid | 100% | 640 | $60 | $38,400 |
| Mobile App Developer | Carlos Mendez | Mid | 100% | 640 | $60 | $38,400 |
| Web App Developer | Aisha Rahman | Mid | 100% | 640 | $60 | $38,400 |
| Mapping & Location Developer | Liam O'Connor | Mid | 50% | 320 | $60 | $19,200 |
| Payment Integration Developer | Sofia Rossi | Senior | 50% | 320 | $75 | $24,000 |
| UI/UX Designer | Hannah Lee | Mid | 40% | 256 | $55 | $14,080 |
| QA Lead | Tomás Silva | Senior | 60% | 384 | $65 | $24,960 |
| QA Tester | Zoe Williams | Junior | 60% | 384 | $40 | $15,360 |
| TOTAL |  |  |  | 4,800 |  | $303,360 |

Table 1: Resource plan — roles, names, skill levels, FTE allocation, estimated hours, rates, and cost.

# 9. Resource & Cost Plan

The cost plan is built bottom-up as the labor comes from the resource plan above, and every other line is estimated individually. Although the project assumes an unlimited budget, this baseline is used to track spending against the plan.

## 9.1 Cost Plan

| Item | Category | Qty/Months | Unit Cost | Duration (months) | Total | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Team labor | Labor | 4,800 hours | $63.20/hour (avg) | 4 | $303,360 | From Table 1 |
| Cloud hosting | Infra | 1/month | $1,200 | 4 | $4,800 | Dev, staging, production |
| Developer tool licenses | Tools | 11 seats | $120/seat | N/A | $1,320 | IDEs, CI/CD, design tools |
| Mapping/navigation API | Third-party | 1/month | $500 | 3 | $1,500 | Usage-based; billing alerts |
| Payment gateway & sandbox | Third-party | 1/month | $300 | 3 | $900 | Test transaction fees |
| SMS/push notifications | Third-party | 1/month | $150 | 3 | $450 | Usage-based |
| Mobile test devices | Equipment | 4 devices | $400 | N/A | $1,600 | QA device lab |
| External security audit | Compliance | one-off | $8,000 | N/A | $8,000 | Before release |
| Contingency | Reserve | 10% | applied to subtotal | N/A | $32,193 | 10% of $321,930 |
| TOTAL BUDGET |  |  |  |  | $354,123 |  |

Table 2: Bottom-up cost plan with 10% contingency.

## 9.2 Budgeted Cashflow (Monthly)

Labor is spread evenly because allocations are held constant for all 16 weeks. Tool licenses and test devices are paid up front, and third-party services start in Month 2, and the security audit is paid in Month 4 before release. Contingency is applied at 10% of each month's spending.

| Category | Month 1 (Wk 1–4) | Month 2 (Wk 5–8) | Month 3 (Wk 9–12) | Month 4 (Wk 13–16) | Total |
| --- | --- | --- | --- | --- | --- |
| Team labor | $75,840 | $75,840 | $75,840 | $75,840 | $303,360 |
| Cloud hosting | $1,200 | $1,200 | $1,200 | $1,200 | $4,800 |
| Tool licenses | $1,320 | $0 | $0 | $0 | $1,320 |
| Third-party services | $0 | $950 | $950 | $950 | $2,850 |
| Test devices | $0 | $1,600 | $0 | $0 | $1,600 |
| Security audit | $0 | $0 | $0 | $8,000 | $8,000 |
| Contingency (10%) | $7,836 | $7,959 | $7,799 | $8,599 | $32,193 |
| Monthly total | $86,196 | $87,549 | $85,789 | $94,589 | $354,123 |
| Cumulative spend | $86,196 | $173,745 | $259,534 | $354,123 |  |

Table 3: Monthly budgeted cashflow across the four-month semester.

# 10. RACI Matrix

The matrix assigns each WBS work package to the roles above. Every row has exactly one Accountable role which is represented with “A”,  and at least one Responsible role which is represented by “R”.

| Work Package | PM | BA | BEL | BED | MOB | WEB | MAP | PAY | UX | QAL | QAT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project planning & schedule (1.7.1) | A/R | C | C | I | I | I | I | I | I | C | I |
| Stakeholder updates (1.7.2) | A/R | R | I | I | I | I | I | I | I | I | I |
| Risk management (1.7.3) | A/R | C | C |  |  |  | I | C |  | C |  |
| Requirements & SRS | A | R | C | I | C | C | C | C | C | C | I |
| UI/UX design | I | C | I |  | C | C |  |  | A/R | I |  |
| Authentication (1.1) | I | C | A | R | R | R |  |  | C | C | I |
| User & operator management (1.2) | I | C | A | R | C | R |  |  | C | C | I |
| Dashboards (1.3) | I | C | C | C | R | A/R | C | C | C | C | I |
| Reporting & analytics (1.4) | I | C | C | R |  | A/R |  | C | C | C | I |
| Mapping & notifications (1.5) | I |  | C | C | R | C | A/R |  | C | C | I |
| Backend/API & database (1.6.1–1.6.2) | I | I | A/R | R | C | C | C | C |  | C | I |
| Payment integration (1.6.3) | I | I | C | C | C | C |  | A/R |  | C | I |
| Security & compliance (1.6.4) | I |  | A/R | R |  |  |  | R |  | C | I |
| Test planning & execution (1.7.4) | I | C | C | C | C | C | C | C | I | A/R | R |
| Deployment & release (1.7.4) | A | I | R | R | R | R | I | I | I | C | I |

Table 4: RACI matrix. R = Responsible, A = Accountable, C = Consulted, I = Informed; A/R means the same role holds both.

Role key

PM = Project Manager; BA = Business Analyst; BEL = Backend/API Lead; BED = Backend/API Developer; MOB = Mobile App Developer; WEB = Web App Developer; MAP = Mapping & Location Developer; PAY = Payment Integration Developer; UX = UI/UX Designer; QAL = QA Lead; QAT = QA Tester